PROJECT LOG

| Project Title: | Music Video | Project Deadline: | Christmas Break |
| --- | --- | --- | --- |

| Job | Deadline | Completed |
| --- | --- | --- |
| Costume | 30th September |  |
| Shot list | FINISHED | FINISHED |
| Story board | 30th September |  |
| Ancillary Research | 17th October |  |
| START FILMING | 20-21th October |  |
| Footage Rush | 20-21th October |  |
| Colour Grading | 24th October |  |
| First Edit | 25th October |  |
| Second Edit | 26th October |  |
| Final Edit | 27th October |  |
| BTS | 22nd October |  |
| Ancillary Production | 6th November |  |
| Evaluation | 9th January 2015 |  |